# Applications Area – July 1 – September 15 2003
Torre Wenaus – Applications Manager

This quarter saw the first important results in integrating applications area software as production software in the experiments.  CMS successfully integrated POOL and SEAL and validated it for event storage in their pre-challenge simulation production. At the end of the quarter they had successfully stored ~1M events with POOL. ATLAS successfully integrated POOL and SEAL in their Release 7, an important milestone towards production use of POOL in ATLAS DC2 in 2004. Both experiments found the integration of POOL and SEAL to require more work than they anticipated. Since it is as vital for the project to see prompt and successful take-up of the software in the experiments as it is to develop the software in the first place – “release early and often” only works if complemented by “integrate early and often” – the project must examine how to increase the (already significant) effort employed to assist the experiments in integration. This will be examined over the next quarter. The next quarter will also see the first integration feedback from LHCb.

Milestone performance was good in most critical path areas (POOL, SEAL) but not so good elsewhere, largely because of insufficient allowance for the holidays – most missed milestones are expected to be completed in October. However, a critical path (for LHCb) milestone is seriously late: the readiness of SPI infrastructure for Windows (cygwin with Visual C++) builds of LCG software. The milestone is late because SCRAM is not yet fully functional in this environment. It is being worked on, but the work would be expedited if CMS SCRAM expertise (recently departed from the project) were applied to its completion.

Project manpower was stable during the quarter. CERN-resident personnel continued to consolidate in building 32 to the great benefit of the project.

A major event of the next quarter will be an internal technical review of the applications area Oct 20-22.

## WBS 1.1.1 - Software process and infrastructure (SPI)

Project Leader: Alberto Aimar, CERN IT/DI

This quarter saw the completion of the first version of all SPI services as in the plan presented at the SC2. An updated plan covering the coming quarters was developed (CERN-LCGAPP-2003-13). In new activity during the quarter, standards and tools for automated packaging and distribution of LCG and external software and documentation were implemented and deployed; quality assurance practices and reports were formalized; and a user workbook with greatly improved documentation was put in place. With the completion of the services suite, SPI is approaching a more steady state mode of operation. Manpower is (just) sufficient to sustain the needed services, but only minimal, most urgent improvements to services will be possible at current manpower levels. We continue to estimate 7-8 FTEs as the level required for a fully robust operation. Staffing was ~5.5 FTEs throughout the quarter, but with a changing distribution of people. Substantial effort was spent to document and collect knowledge from the people that moved from SPI to other projects or back to their LHC experiment. Quality assurance activities will be the main focus of the next quarter, as well as better defining uniform policies to be followed by the projects.

The only SPI level 2 milestone for the quarter, support for a Windows binary version of LCG software, is incomplete because SCRAM does not yet work under cygwin. All other aspects of the work are complete. It is being worked on, but the work would be expedited if CMS SCRAM expertise (recently departed from the project) were applied to its completion. It is an important milestone because LHCb requires Windows binary builds in order to do LHCb integration of LCG software.

Highlights from the quarter follow.

Software distribution service: SPI has added a service to allow easy downloading and local installation of the LCG software and all needed external software. From the SPI web any user can select Pool and Seal in the version wanted and the product will be downloaded, as well as all the right versions of the external software used. This greatly simplifies the work of LCG users and developers that are not using the development setup available from the LCG Application Area at CERN. The service also installs locally the right configuration of Scram, so developers can modify and easily build locally the LCG software.

Policies and quality assurance: QA activities were increased as was the definition of policies and guidelines: for coding and design, for standard CVS structure and for releasing and building software. These policies are now stable. SPI is actively encouraging LCG projects to use the LCG development guidelines and testing practices. SPI is setting up QA infrastructure to verify the quality of the LCG software. The QA framework is under definition and is it being automated in order to collect software metrics and verify adherence to the LCG policies. This activity still suffers from the fact that resources assigned to it have changed due to causes external to SPI, but has been one of the SPI focuses of this quarter. “QA reports” have been written studying the major Pool and Seal releases and will become a regular practice.

LCG workbook: All SPI services have greatly improved their documentation on the web and

SPI is now actively maintaining the LCG Workbook web site. This workbook is developing into a comprehensive and complete documentation of all the LCG projects. Each project provides a web section in terms of practical “How To” pages that guides the LCG users and developers in all their activities with LCG software and within LCG projects. In this quarter SPI has provided the first version of its workbook, receiving positive feedback from the users.

Testing framework: SPI has continued the deployment of a testing framework to standardize the way projects perform unit, regression and integration testing. CppUnit and Oval are now effectively used, and PyUnit is supported for testing of Python applications.  QMtest was chosen to integrate all the test execution and reporting. It runs all tests of a project via a single script or a web interface.

External software service: The service now provides more than fifty packages in the versions and platforms needed by the LCG projects. SPI has defined a standard procedure to provide these installations and a well documented website for documenting the external software installed. An important achievement was provision of support of the Intel compilers on Linux (icc, 32 bits, ecc 64 bits) and for the Windows operating system (vsc++ 7), which required the installation of all software needed by the LCG projects and experiments for those compilers. Another major improvement is the integration of the service with the Software Download Service.

Savannah portal: This service is now in use by all the LCG projects and by more than fifty projects in the LHC experiments (from thirty in June). In order to benefit from the improvements of the open source project of Savannah by the Gnu Foundation, in this quarter SPI has worked in close collaboration with the open source developers to merge all our changes with the open source and then contribute to, and benefit from, the open source as much as possible. To this end one of the principal GNU Savannah developers is visiting SPI at CERN for the month of September. As the service had reached a stable level and the staff responsible is under change the development is reduced to minimal bug fixing. The effort is focused on convergence with the Savannah open source project. Next quarter there will be major improvements to answer to several user requests.

Scram: In this quarter, as in the previous one, the main task of SPI was to improve Scram performance, work on the port to Windows and help all the LCG projects to use Scram in their releases. Scram had one bug fix release in order to fulfil requirements specified in the LCG development policies.  Scram is also integrated with the Software Download service so that developers can use Scram also on their local computer. As mentioned above, the still incomplete porting of SCRAM to Windows cygwin is a serious missed milestone. A long term strategy for configuration and build management taking into account the experience gained so far with SCRAM usage, development and support will be developed in the next quarter.

Automatic build service: An important new development was the integration in the release cycles of an automatic build system. In this quarter the adaptation and deployment of NICOS for automated POOL and SEAL software builds was completed.

Code documentation service: We improved the automatic system to generate code documentation (Doxygen, LXR and ViewCVS) by also collecting log information on the operations done on the repository (commits, updates, etc) and increasing its configurability by each project. Support for PI and for and for the Simulation projects was added. This service is stable and there will be only minor changes in the coming quarters in order to adapt it to the coming IT CVS service.

## WBS 1.1.2 - Persistency framework (POOL)

Project Leader: Dirk Duellmann, CERN IT/DB

The focus of the POOL effort for the quarter was support for the integration and deployment of POOL in CMS and ATLAS as the mechanism for production event storage. Following the release of the first production version of POOL last quarter, the measure of success now shifts to successful integration, validation and deployment of POOL in the experiments, towards which POOL has worked to promptly address the inevitable problems as they are uncovered during integration. The first important validation milestones were met on time with the acceptance and deployment of POOL by CMS for its pre-challenge simulation production. ATLAS also delivered its first integration of POOL into Athena during the quarter. Both ATLAS and CMS found the integration of POOL and SEAL to be more work than they expected; the project will be examining how best to help the experiments further in integration in the future in order to ensure that project software is integrated and validated promptly.

During the quarter POOL produced several releases starting with 1.2.0 which fulfilled new feature requests originating from the experiment integration efforts. POOL 1.2.0 included on the storage manager side for the first time support for the special vector<bool> type and also supported iteration over uncommitted objects already during the originating transaction. Several modifications to the casting and conversion operations provided by POOL Refs which were requested by CMS went into this release. It also supported the ATLAS request for a customisable ownership policy in the POOL cache to allow easier integration into StoreGate.

One of the original release goals was to introduce performance testing for all components. This has been achieved, though a thorough optimisation based on these tests has only happened in some components so far. For the ROOT based collection implementation we were able to show that POOL only imposes very limited overhead on top of vanilla ROOT. Because of the continuing workload on implementing new features, other work packages have not yet achieved the same level of understanding of their performance.

POOL V1.2.1 was released mainly to pick up the ROOT bug-fix version 3.05.07a. POOL V1.3.0 was targeted mainly to pick up the SEAL 1.1.0 release which came with significant enhancements (and also some API changes) in several of the components used by POOL. In particular the use of the message service had to be adapted in POOL to adjust to the new model. The following releases 1.3.1, 1.3.2 and 1.3.3 were mainly bug-fix releases issued on request from the experiments to remove smaller issues described in (http://pool.cern.ch/relnotes.html).

No significant changes occurred in POOL staffing during the quarter.

## WBS 1.1.3 – Core libraries and services (SEAL)

Project Leader: Pere Mato, CERN EP/SFT

During the quarter we released, with only a small delay with respect to the planned date, version 1.0.0 of the SEAL software incorporating a number of essential elements that makes the release ready for use in experiment frameworks. In addition to this release, a number of technical and bug fix versions have also been released (0.3.3, 0.3.4, 1.1.0) in light of user feedback, particularly the integration efforts in the experiments. The quarter saw the initiation of design work for an important pending component foreseen for SEAL, the object whiteboard. Here follow the main highlights for each work package.

- Foundation libraries. No new functionality was added to the foundation libraries. Bug fixes and improvements were made in various areas such as the plug-in manager. Some changes were made to better support new platforms.

- Math Libraries. Continued the development of the new Minuit package. In particular the development of a tutorial (taken from one of Fred James’ lectures), improvements in minimizing the number of function evaluations, and changes in the user interface to configure the number of iterations, the edm-value and adding the possibility for fixing and releasing user parameters. Installation of new versions of math related packages in the SPI external area (CLHEP, GSL, Blas, Lapack).

- LCG Dictionary. Apart from bug fixes, several features for the Dictionary work-package have been implemented including support for enums, optional arguments in function calls, the possibility to concatenate calls to ReflectionBuilder functions, and support for the PluginManager. Ready-to-use dictionaries have been created for STL (vector, list for integral types including string), CLHEP (Vector and Random) and the Reflection package itself. The latter makes it possible e.g. to use the dictionary information through the python binding. The STL and CLHEP dictionaries will be extended upon request of users.

- Basic Framework services. We have released the first implementation of the SEAL component model. The Framework sub-system is populated with two new packages (SealKernel, SealServices) containing the base classes and services for the model. A first batch of corrections to this young model has already been applied. More work is being done at present towards the building of more SEAL services as DictionaryService to provide on-demand loading of SEAL C++ dictionaries and others. We are eager to receive usability feedback from LCG projects (POOL, PI, Simulation) and from the experiments.

- Scripting Services. The report of the evaluation of the existing products for generating Python bindings has been made public. The conclusion is that Boost, Python and SWIG are the leading candidates, by virtue of providing the greatest coverage of features, the most complete documentation, and being under active maintenance and development. Most imaginable features are supported by both, and it seems likely that both systems will continue to improve with time. It is recommended that a more detailed analysis of the issues surrounding interoperability of the two technologies be carried out and this investigation has been started. The PyLCGDict package providing the Python binding to the LCG Dictionary has been released. It allows the user to interact with any C++ class for which the LCG Dictionary has been generated. Optimisation and C-style array support was added to PyROOT.

- Documentation and Education. Building on the foundation of the pilot Python course, the course material was developed and adjusted. Three new Python courses were run as part of the CERN technical training program. In liaison with SPI, the SEAL workbook structure and creation procedures were re-designed and streamlined. A variety of new features available in release 1.0.0 were documented in how-tos.

- Software Process and Infrastructure. More efforts have been put in the QA activities in the last quarter. Every SEAL package contains a tests sub-directory, with unit tests covering a large amount of code. The existing unit tests in the Foundation subsystem have been converted to use the CppUnit and the new tests in the Framework and Scripting have been also written using CppUnit following the policies proposed by SPI. All SEAL tests have been integrated in QMtest driver, which gives the possibility to easily run the tests and visualize the results.  Automatic builds of all the SEAL software are performed every night using the NICOS service. Progress has been made to support builds for new platforms and compilers (icc and windows) but unfortunately this work has not been completed and we have not yet a release including these new platforms.

The milestone to establish a formal decision-making process for the selection of external software, already twice postponed due to its low priority (arising from a lack of perceived need; we have not significantly felt the lack of it), has been demoted to a level 3 milestone because of its low relative importance. We anticipate that important new milestones for SEAL will be defined in the next quarter in areas relating to the object whiteboard and to grid-based services supporting distributed analysis (following ARDA outcomes).

## WBS 1.1.4 – Physicist Interface (PI)

Project Leader: Vincenzo Innocente, CERN EP/SFT

During the quarter the work continued to focus on the Analysis Services work package, consistent with the guidelines from SC2 and further guidance arising from a July status report PI presented to the SC2. Priority was given to completing the implementation of all AIDA binned histograms (Histogram1D/2D/3D and Profile1D/2D) as wrappers to their corresponding ROOT objects. This functionality, including the corresponding examples, was released as version 0.3.0 of PI on July 15.

Following feedback from CMS, the functionality of the Proxy_Store component has been improved, now allowing for storing/retrieving groups of histograms using std::vector's or std::map's. Together with some small bug-fixes, and changes in the configuration adapting to new versions of SEAL and ROOT, this was released as version 0.4.0 on Aug. 29. This release was followed by another release (0.4.1) on Sep. 9 where mainly configuration changes (SEAL 1.1.0) and some bug-fixes contributed by LHCb were integrated.

The work on the AIDA evaluation and report is delayed mainly because of slow feedback from users in the experiments (partially due to holiday season, of course). From the feedback we did receive, it is clear that there is interest in using AIDA/PI. We will actively follow the contacts we have now established to collect feedback and estimate to be able to finish the report before end October.

Ongoing work concentrates on updating the PI test suite to full SPI compliance. This is expected to be finished by mid October and will result in the 1.0.0 release. Further planning of the future PI work plan will follow the outcome of the ARDA RTAG.

## WBS 1.1.5 – Simulation

Project Leader: T. Wenaus, BNL/CERN EP-SFT

During this quarter the strong activity initiated last quarter in the Physics Validation, Geant4 and Generator Services subprojects continued, with all projects showing good participation by and support from the experiments. The FLUKA team is collaborating effectively with the Physics Validation activity. The Generic Framework activity continues to develop slowly among the experiment simulation leaders. A series of reports on all project activities were presented in applications area meetings in July and August, and the projects were discussed in the following Architects Forum meetings.

The Generic Simulation Framework subproject (A. Dell’Acqua) continues to develop slowly. As a discussion forum among the experiment simulation leaders it is proving to be a very efficient way of exchanging information and profiting from one another’s results and experience. A high level service architecture has been laid out, with the “glue” connecting the services to one another and to basic services such as persistency coming from the framework infrastructure (SEAL). Design work on the services is underway, with the starting points being existing applications.  Principal future steps are evaluation of the ALICE virtual monte carlo and the implementation of a prototype in close collaboration with the physics validation subproject to provide them with a working infrastructure for comparisons/tests with different engines. Further progress on design and optimal implementation approach is best achieved through hands-on experimentation in the context of the planned prototype; therefore the “Generic framework high level design and implementation approach defined” milestone has been superseded by a milestone for the availability of an initial prototype by the end of the year. The high level design and project status were presented in an applications area meeting in August. The effort level remained as the available time of the experiment simulation leaders during the quarter.

The Geant4 subproject (J. Apostolakis) support activities were the largest part of the efforts during the quarter.  Following up release 5.2 in June, the expanding testing of CMS and LHCb, and feedback from other users, a number of bugs and deficiencies were uncovered.  The investigation of problems in geometry and hadronics and the creation of fixes and accompanying testing were significant undertakings. In a series of meetings with SPI, initial areas for cooperative work were identified – the Savannah portal and SPI testing infrastructure. Active collaboration on infrastructure is planned to start in October. The workplan for the subproject (linked from the subproject web page) was updated during the quarter.

In geometry (WP-1), development of a twisted trapezoid solid reached the stage of identifying the candidate solution. A detailed URD traceability matrix is pending. A first implementation of volume divisions for tubs, box, cons has been created. The development of weight-window biasing and its documentation have been achieved ahead of schedule (it was Q4).

Improvements in the presentation of the results of system testing (WP-2) are pending.  A first security assessment was made of the vulnerabilities of the testing system, and the most important patches needed were identified.

The testing of the model approach for EM physics (WP-3) has been extended substantially. The identification of the set of tests is pending.  Testing results were reported at the Geant4 Workshop September 2nd-6th at Vancouver. An initial statistical test was created from the Atlas FCAL test beam, with the assistance of its team. The development of the error propagation module prototype has made large steps towards its expected first prototype release, scheduled for end September. These were reported at the Geant4 Workshop.

The development of leading particle biasing and X-section biasing in the hadronics (WP-4) has been undertaken. The first physics lists specifically for the simulation of LHC experiments have been published.

Follow-up of new requirements (WP-5) from CMS regarding direct linkage of simulated particle tracks with the primaries from an event generator was undertaken.  The resulting developments were done by SLAC-based Geant4 developers and kindly made available very quickly for testing and the creation of a customized release by CMS. A first meeting on performance with experiments took place and identified areas for investigation and improvement of information for performance and memory allocation monitoring.

There are two departures at the end of this quarter. M Dressel reached the end of his fellowship (G Daquino is to take over his developments). P Mendez (LCG Spain) is departing.

There was one arrival, Oliver Link started in July and is working in geometry and field. The effort level in the subproject was ~9 FTEs at the end of the quarter.

The FLUKA Integration subproject (A. Ferrari) continued to be active with the physics validation subproject. Activity in generic framework integration awaits the better definition of that project, with the expectation that work done for ALICE integration can be reused. FLUKA plans and milestones were presented in an applications area talk.

The Physics Validation subproject (F. Gianotti) continued to be very active in the last quarter. The project continues a regular program of monthly meetings gathering participants from all the LHC experiments and simulation projects. Activity during the quarter covered the following areas:

      - Simple benchmarks. The study of double differential cross-sections for (p, xn) at various energies and angles has been completed. FLUKA and G4 have been compared with many experimental measurements performed at Los Alamos. A note summarising the results is being written. The next benchmark to be addressed is pion absorption.

      - Physics requirements of the various experiments are being revisited. The ATLAS part is completed. We anticipate this to be completed for all experiments by the end of the year.

      - Radiation background studies in the LHCb experiment, aiming at   comparing G4/FLUKA/GCALOR, have started.

      - Physics validation of FLUKA using ATLAS Tilecal test beam data has started.

      - Validation of EM physics is essentially completed, although new test beam data and studies are available and are regularly reported to our meetings. In particular, results on shower shapes in the ATLAS EM calorimeter have recently been obtained.

      - Comparisons of test beam data with G4 to validate the hadronic physics are going on. They are based on the calorimeters of both ATLAS and CMS as well as special data collected with the ATLAS pixel detector.

Effort level was stable through the quarter at ~3 FTEs.

The Generator Services subproject (P. Bartalini) continued to be very active in the quarter. Dedicated subproject meetings are held monthly. The manpower level was stable during the quarter at 1.3 FTEs. MC4LHC (which oversees the activities of the project) issued series of recommendations that will be taken into account in future planning:

## The organization and goals of the subproject, the defined milestones, the current GENSER structure and the plans for its future evolution have been approved.

## The LCG participation in the MC4LHC workshop has been appreciated. LCG Generator is contributing to advertise the new MC projects and is providing a forum for discussions on the generator related software.

## It is recommended to improve the collaboration with the MC authors, identifying contact persons to monitor inclusion of packages in the LCG environment.

## The turnover and the possible loss of well trained people (for instance the librarian) can represent a big problem as all the experiments will soon rely on GENSER. Long term support to LCG Generator members has to be guaranteed by LCG.

Highlights during the quarter follow.

Generator library (WP1): The beta version of GENSER containing the top priority packages (HERWIG, HIJING, ISAJET and PYTHIA) was prepared during the quarter. Contact persons for these MC projects have been identified. Package versions pursued for inclusion have been indicated by the contact persons in MC projects and/or by the volunteered beta testers in the LHC experiments.

GENSER beta will be released on schedule at the end of September. A pre-release was produced in August. CMS and ATLAS have reported very positive feedback to the September monthly meeting. The use of the Simulation Savannah portal for bug report and task assignment will be strongly encouraged from now on.

Following the suggestions from the contact persons in LHC experiments and MC projects, three milestones relevant to WP1 are being defined:

- The inclusion of the first C++ generator (end of 2003). Sherpa is the identified candidate (contact person F.Krauss). Sherpa has been already successfully installed as external package in the LCG environment.

- The inclusion of LHAPDF (end of January 2004). LHAPDF is considered to have the highest priority among the remaining mandated packages.

3)   The inclusion of COMPHEP, ALPGEN and EVTGEN (end of March 2004).

Dedicated LCG resources corresponding to 1.0 FTE for 0.5 years would be needed to take on these tasks.

Storage, event interfaces and particle services (WP2): The CLHEP split is complete and the LHC experiments are currently performing its evaluation. It may be necessary to support a dedicated LHC version of HepMC but it is currently premature to take a decision. An agreement on the persistency for the generator output would be necessary to organize the work. Different solutions are currently being discussed in LCG generator meetings. A specific proposal will be produced end of November 2003. Dedicated LCG resources corresponding to 0.5 FTE for 1.0 years may be necessary to coordinate the standardization of HepMC.

Common event files, event database (WP3): MCDB will be the tool for centrally providing common event generator files. MCDB has a web interface providing simple access to event files, and a programming interface. The impact of the choice for the common event format on MCDB will have to be carefully evaluated. Technical support for bookkeeping and for the storage and management of large files will be needed from LCG.

Tuning and validation of event generators (WP4): progress has been made in the context of the MC4LHC workshop held this summer at CERN. However setting up a dedicated project in LCG does require the generator library to be in place. A specific proposal for the integration of existing tools in the LCG environment will be made in 2004. The JetWeb project [hep-ph/0210404] should constitute a good starting point for this work package.

JetWeb is a Database of data, MC and comparisons with fitting and tuning tools. An enquiry is currently being made to verify if the JetWeb authors are interested to use GENSER and/or to develop their project in LCG.

It is anticipated that dedicated LCG resources will be requested in 2004.

## WBS 1.1.6 - ROOT participation

The LCG applications area contributes effort to the ROOT project. The LCG-contributed effort to mainstream ROOT development areas liberates the core members of the ROOT team to devote greater time to the specialized developments in ROOT I/O and elsewhere that are required by LCG software. Ilka Antcheva and Valeriy Onouchine are LCG-supported personnel contributing to GUI development, documentation, and a new implementation of ROOT on Windows using Win32GDK. During the quarter the ROOT team continued to collaborate with POOL participants and experiment integrators to respond to integration feedback and bug reports. The ROOT team also began an examination of how POOL uses ROOT I/O in its streaming layer in order to identify any shortcomings and recommend improvements. In addition, Gerardo Ganis (working with ALICE and ROOT) continued work on the integration of Grid-based authentication into ROOT, now officially documented and released (http://root.cern.ch/root/Auth.html).

## WBS 1.1.7,1.18 – Core/Grid Interface & Experiment Integration

Through this activity the Applications Area provides direct assistance to the experiments at the interface between core software and the grid, and supports the adaptation of physics applications to the grid environment. Oxana Smirnova continued work with ATLAS on the integration and deployment of ATLAS simulation and reconstruction production on the grid, with the focus now moving to the LCG-1 service. She also continued to play an active role in the GAG HEPCAL activities. Gerardo Ganis works with ALICE and the ROOT team on different aspects of Grid-enabling ROOT as discussed earlier.

## Milestone performance during the quarter

WBS 1.1.1 - SPI:

- SPI support for Windows binary version of LCG software (Aug)

  - Incomplete due to ongoing SCRAM difficulties (non-SCRAM aspects are done). Anticipate October.

WBS 1.1.2 - POOL:

- CMS POOL integration: POOL persistency of CMS event (Jul)

  - Completed

- Initial POOL deployment on LCG-1 (Jul)

  - Incomplete due to late availability of LCG-1. In progress.

- ATLAS POOL integration: POOL persistency in Release 7 (Aug)

  - Completed

WBS 1.1.3 - SEAL:

- First set of GSL enhancements available (Sep)

  - GSL enhancements were delivered but statement on GSL and NAG usage still required. New milestone (Oct) added for this; this one closed.

- SEAL V1.0 release (Jul)

  - Completed

- Nightly builds deployed in SEAL (Jul)

  - Completed

- Establish external software decision process (Sep)

  - Postponed due to higher priorities and demoted to level 3

- Math library workplan in place (Jul)

  - Incomplete. Promised for ~end Sep.

- SEAL support for Windows binaries (Sep)

  - Incomplete pending SPI milestone completion. Anticipate October.

WBS 1.1.4 - PI:

- AIDA interface review (users) completed (Sep)

  - Incomplete due to slow feedback. Anticipate completion in October.

WBS 1.1.5 - Simulation:

- Generic framework high level design and implementation approach defined (Jul)

  - Superseded by an initial prototype milestone for Dec

- Simulation physics requirements revisited (Jul)

  - Completed for ATLAS; should be complete for all experiments by end of year

## Upcoming milestones (to level 2)

WBS 1.1.1 - SPI:

- SPI support for Windows binary version of LCG software (Oct)

- SPI infrastructure operational on IT CVS service (Nov)

WBS 1.1.2 - POOL:

- POOL RDBMS independence layer in beta (Sep)

- POOL support for Windows binaries (Oct)

- Initial POOL deployment on LCG-1 (Nov)

WBS 1.1.3 - SEAL:

- Math library workplan in place (Oct)

- Statement on GSL and NAG usage for math library (Oct)

- SEAL support for Windows binaries (Oct)

WBS 1.1.4 - PI:

- Report from AIDA interface review (Oct)

WBS 1.1.5 - Simulation:

- SPI-G4 collaborative infrastructure pilot in place (Nov)

- Initial generic simulation prototype supporting Geant4 and FLUKA (Dec)

- Simulation physics requirements revisited for all experiments (Dec)